## TC-Overview
Project Name : | Recommender System based on collaborative filtering
Test: | TC-2
Test Case Scenario : | Login/Account Security
Created by : | Muhamad Amir Akmal
Remarks:
Pre-Condition : | Already have an account created
Test CaseID : | Test Case Description | Pass/Fail: | Date Completed:
TC-2.1.1 | Test Login button on the top right (next to sign up) | Pass | 2023-04-27
TC-2.1.2 | Test Login button in the middle left (next to sign up now) | Fail | 2023-04-27
TC-2.2.1 | Login using correct email and password for Individual | Pass | 2023-04-27
TC-2.2.2 | Login using incorrect email and correct password for Individual | Pass | 2023-04-27
TC-2.2.3 | Login using correct email and incorrect password for Individual | Pass | 2023-04-27
TC-2.2.4 | Try Individual login in with the correct password but the alphabets in different Caps | Pass | 2023-05-03
TC-2.2.5 | Try Individual login with email in caps | Pass | 2023-04-29
TC-2.2.6 | Try Individual login in with empty email field and correct password | Pass | 2023-04-30
TC-2.2.7 | Try Individual login in with correct email and empty password field | Pass | 2023-04-30
TC-2.2.8 | Try to bypass 2FA verification for Individual login by trying to enter without the verification code | Pass | 2023-04-30
TC-2.2.9 | Enter correct 2FA code sent by RECS site for Individual login | Pass | 2023-04-27
TC-2.2.10 | Enter incorrect 2FA Code for Individual login | Pass | 2023-04-28
TC-2.2.11 | Enter partial 2FA Code for Individual login | Pass | 2023-04-29
TC-2.2.12 | Click on "RECS" on top left of the 2FA verification page for Individual login | Pass | 2023-05-06
TC-2.3.1 | Login using correct email and password for Organization | Pass | 2023-04-27
TC-2.3.2 | Login using incorrect email and correct password for Organization | Pass | 2023-04-27
TC-2.3.3 | Login using correct email and incorrect password for Organization | Pass | 2023-04-27
TC-2.3.4 | Try Organization login in with the correct password but the alphabets in different Caps | Pass | 2023-05-05
TC-2.3.5 | Try Organization login with email in caps | Pass | 2023-05-05
TC-2.3.6 | Try Organization login in with empty email field and correct password | Pass | 2023-05-05
TC-2.3.7 | Try Organization login in with correct email and empty password field | Pass | 2023-05-05
TC-2.3.8 | Try to bypass 2FA verification for Organization login by trying to enter without the verification code | Pass | 2023-05-05
TC-2.3.9 | Enter correct 2FA code sent by RECS site for Organization login | Pass | 2023-04-27
TC-2.3.10 | Enter incorrect 2FA Code for Organization login | Pass | 2023-05-05
TC-2.3.11 | Enter partial 2FA Code for Organization login | Pass | 2023-05-05
TC-2.3.12 | Click on "RECS" on top left of the 2FA verification page for Organization login | Pass | 2023-05-06
TC-2.4.1 | Login using correct email and password for Admin | Pass | 2023-04-27
TC-2.4.2 | Login using completely incorrect email for Admin | Pass | 2023-04-28
TC-2.4.3 | Login using completely incorrect password for Admin | Pass | 2023-04-28
TC-2.4.4 | Try Admin login in with the correct password but the alphabets in different Caps | Pass | 2023-05-05
TC-2.4.5 | Try Admin login with email in caps | Pass | 2023-05-05
TC-2.4.6 | Try Admin login in with empty email field and correct password | Pass | 2023-05-05
TC-2.4.7 | Try Admin login in with correct email and empty password field | Pass | 2023-05-05
TC-2.4.8 | Try to bypass 2FA verification for Admin login by trying to enter without the verification code | Pass | 2023-05-05
TC-2.4.9 | Enter correct 2FA code sent by RECS site for Admin login | Pass | 2023-04-27
TC-2.4.10 | Enter incorrect 2FA Code for Admin login | Pass | 2023-05-05
TC-2.4.11 | Enter partial 2FA Code Admin login | Pass | 2023-05-05
TC-2.4.12 | Click on "RECS" on top left of the 2FA verification page for Admin login | Pass | 2023-05-06
TC-2.5.1 | Upon landing on the login page, multiple fast clicks on Sign In button | Pass | 2023-04-30
TC-2.5.2 | Enter a valid email and password, then click "sign in" button multiple times | Pass | 2023-05-05
TC-2.5.3 | Click on "Forgot Password?" | Pass | 2023-05-13
TC-2.5.4 | On "Forget Password" page, click verify with empty email field | Pass | 2023-05-13
TC-2.5.5 | On "Forget Password" page, enter incorrect email | Pass | 2023-05-13
TC-2.5.6 | On "Forget Password" page, enter correct email | Pass | 2023-05-13
TC-2.5.7 | On verify email page, enter the verification code received | Pass | 2023-05-13
TC-2.5.8 | On "Forget Password" page, leave password field blank and try to update | Pass | 2023-05-14
TC-2.5.9 | On "Forget Password" page, enter different passwords into the two fields | Pass | 2023-05-14
TC-2.5.10 | On "Forget Password" page, entersame passwords but not in suggested format | Pass | 2023-05-14
TC-2.5.11 | On "Forget Password" page, enter correct new passwords | Pass | 2023-05-14
Formulas:
Date Completed: = [Date Completed:, row above]

## TC-2.1.1
Project Name : | Recommender System based on collaborative filtering
Test CaseID : | TC-2.1.1
Test Case Description : | Test Login button on the top right (next to sign up)
Created by : | Muhamad Amir Akmal
Remarks: | Already at RECS website main landing page
Pre-Condition : | N.A
Test Step | Test Step Description | Test Data | Expected Results | Actual Result | Pass/Fail | Remarks
TC-2.1.1.1 | Press Login button on the top right next to Sign Up button | Nil | User should be redirected to the login page | The website redirects user to the Login page | Pass | nil

## TC-2.1.2
Project Name : | Recommender System based on collaborative filtering
Test CaseID : | TC-2.1.2
Test Case Description : | Test Login button in the middle left (next to sign uTest Login button in the middle left (next to sign up now)
Created by : | Muhamad Amir Akmal
Remarks: | Already at RECS website main landing page
Pre-Condition : | N.A
Test Step | Test Step Description | Test Data | Expected Results | Actual Result | Pass/Fail | Remarks
TC-2.1.2.1 | Press Login button in the middle of the page under the description, next to the "Sign Up Now" button | Nil | User should be redirected to the Login page | Page broke and website returned "Page lost" | Fail | Already informed Travis of the error

## TC-2.1.3
Project Name : | Recommender System based on collaborative filtering
Test CaseID : | TC-2.1.3
Test Case Description : | Test Login button in the middle left (next to sign uTest Login button in the middle left (next to sign up now)
Created by : | Muhamad Amir Akmal
Remarks: | Already at RECS website main landing page
Pre-Condition : | N.A
Test Step | Test Step Description | Test Data | Expected Results | Actual Result | Pass/Fail | Remarks
TC-2.1.3.1 | Press Login button in the middle of the page under the description, next to the "Sign Up Now" button | Nil | User should be redirected to the Login page | User gets redirected to the login page | Pass | nil

## TC-2.2.1
Project Name : | Recommender System based on collaborative filtering
Test CaseID : | TC-2.2.1
Test Case Description : | Login using correct email and password for Individual
Created by : | Muhamad Amir Akmal
Remarks: | Already at RECS Login page
Pre-Condition : | Already have an Individual account created
Test Step | Test Step Description | Test Data | Expected Results | Actual Result | Pass/Fail | Remarks
TC-2.2.1.1 | Enter the correct email address of registered Individual user account | Email = muhamad.amir.akmal@gmail.com | The email field is able to fill up properly with no issues, dispalying entered email address | The email field is able to be filled and displays "muhamad.amir.akmal@gmail.com" | Pass
TC-2.2.1.2 | Enter the correct password of registered Individual user account | Password = P@$$w0rd | The password field is able to fill up properly with no issues and the password should not be visible to user | The password field is able to be filled up and only small black dots are seen | Pass | The good thing is that the password is hidden even as it is being typed out unlike some other sites where you can still see the characters as they are typed.
TC-2.2.1.3 | Press the "Sign In" button | nil | User should be redirected to 2FA verification page | The login page redirects to a verification page asking for 6 digit code sent to user as a form of 2FA verification | Pass

## TC-2.2.2
Project Name : | Recommender System based on collaborative filtering
Test CaseID : | TC-2.2.2
Test Case Description : | Login using incorrect email and correct password for Individual
Created by : | Muhamad Amir Akmal
Remarks: | Already at RECS website Login page
Pre-Condition : | Already have an Individual account created
Test Step | Test Step Description | Test Data | Expected Results | Actual Result | Pass/Fail | Remarks
TC-2.2.2.1 | Enter an incorrect email address | Email = testingind@gmail.com | The email field should still be able to fill up properly with no issues, dispalying incorrect email address | The email field is able to be filled and displays "testingind@gmail.com" | Pass
TC-2.2.2.2 | Enter the correct password of registered Individual user account | Password = P@$$w0rd | The password field is able to fill up properly with no issues and the password should not be visible to user | The password field is able to be filled up and only small black dots are seen | Pass | The good thing is that the password is hidden even as it is being typed out unlike some other sites where you can still see the characters as they are typed.
TC-2.2.2.3 | Press the "Sign In" button | nil | Remain on login page and there should be an invalid login message displayed | The page still remains on the login page, there is "Invalid login details" message in red. Email and password fields also got cleared | Pass | From user standpoint the red error message helps draw the user attention letting them know why they can't log in. From security standpoint generic error message and clearing of both input fields are good as it makes it harder for attackers find out which credential is right/wrong.

## TC-2.2.3
Project Name : | Recommender System based on collaborative filtering
Test CaseID : | TC-2.2.3
Test Case Description : | Login using correct email and incorrect password for Individual
Created by : | Muhamad Amir Akmal
Remarks: | Already at RECS website Login page
Pre-Condition : | Already have an Individual account created
Test Step | Test Step Description | Test Data | Expected Results | Actual Result | Pass/Fail | Remarks
TC-2.2.3.1 | Enter the correct email address of a registered Individual user account | Email = muhamad.amir.akmal@gmail.com | The email field is able to fill up properly with no issues, dispalying entered email address | The email field is able to be filled and displays "muhamad.amir.akmal@gmail.com" | Pass
TC-2.2.3.2 | Enter the incorrect password | Password = 3434 | The password field is should still be able to fill up properly with no issues and the incorrect password should not be visible to user | The password field is able to be filled up and only small black dots are seen, incorrect password typed is not seen | Pass | The good thing is that the password is hidden even as it is being typed out unlike some other sites where you can still see the characters as they are typed.
TC-2.2.3.3 | Press the "Sign In" button | nil | Remain on login page and there should be an invalid login message displayed | The page still remains on the login page, there is "Invalid login details" message in red. Email and password fields also got cleared | Pass | Error in red is good as it catches the user's eyes and informs them of the login error. From a security standpoint it is good that the error message is generic and the input fields are also cleared so as to not let attackers know which entered credential is right/wrong.

## TC-2.2.4
Project Name : | Recommender System based on collaborative filtering
Test CaseID : | TC-2.2.4
Test Case Description : | Try Individual login in with the correct password but the alphabets in different Caps
Created by : | Muhamad Amir Akmal
Remarks: | Already at RECS Login page
Pre-Condition : | Already have an Individual account created
Test Step | Test Step Description | Test Data | Expected Results | Actual Result | Pass/Fail | Remarks
TC-2.2.4.1 | Enter the correct email address of registered Individual user account | Email = muhamad.amir.akmal@gmail.com | The email field is able to fill up properly with no issues, dispalying entered email address | The email field is able to be filled and displays "muhamad.amir.akmal@gmail.com" | Pass
TC-2.2.4.2 | Enter the correct password of registered Individual user account except the alphabets in different caps, to test if website authorizes login when it shouldn’t | Password = P@$$w0rd | The password field is able to fill up properly with no issues and the password should not be visible to user | The password field is able to be filled up and only small black dots are seen | Pass | The good thing is that the password is hidden even as it is being typed out unlike some other sites where you can still see the characters as they are typed.
TC-2.2.4.3 | Press the "Sign In" button | nil | The website should not authenticate and redirect to the 2FA verification page as the password is in the wrong caps | The website remains on the login page, there is "Invalid login details" message in red. Email and password fields also got cleared | Pass | Site is able to recognize that same password but in different caps for the alphabet characters does not equal to the same registered password and does not authorize login, which is good and helps limit breaching vectors for the login

## TC-2.2.5
Project Name : | Recommender System based on collaborative filtering
Test CaseID : | TC-2.2.5
Test Case Description : | Try Individual login with email in caps
Created by : | Muhamad Amir Akmal
Remarks: | Already at RECS Login page
Pre-Condition : | Already have an Individual account created
Test Step | Test Step Description | Test Data | Expected Results | Actual Result | Pass/Fail | Remarks
TC-2.2.5.1 | Enter the correct email address of registered Individual user account just in different caps | Email = MUHAMAD.amir.akmal@gmail.com | The email field is able to fill up properly with no issues, dispalying entered email address | The email field is able to be filled and displays "MUHAMAD.amir.akmal@gmail.com " | Pass
TC-2.2.5.2 | Enter the correct password of registered Individual user account | Password = P@$$w0rd | The password field is able to fill up properly with no issues and the password should not be visible to user | The password field is able to be filled up and only small black dots are seen | Pass | The way the password is hidden even as it is being typed out is a good implemented idea unlike some other sites where you can still see the characters as they are typed.
TC-2.2.5.3 | Press the "Sign In" button | nil | The website should authorize login and redirect to 2FA verification page as email is not caps sensitive | The website authorizes login and redirects as per usual to the 2FA verification page | Pass

## TC-2.2.6
Project Name : | Recommender System based on collaborative filtering
Test CaseID : | TC-2.2.6
Test Case Description : | Try Individual login in with empty email field and correct password
Created by : | Muhamad Amir Akmal
Remarks: | Already at RECS website Login page
Pre-Condition : | Already have an Individual account created
Test Step | Test Step Description | Test Data | Expected Results | Actual Result | Pass/Fail | Remarks
TC-2.2.6.1 | Leave the email field blank | nil | Nothing should happen as the "Sign In" button has not been clicked, email field remains empty | Nothing happens since it was left blank | Pass
TC-2.2.6.2 | Enter the correct password of registered Individual user account | Password = P@$$w0rd | The password field is able to fill up properly with no issues and the password should not be visible to user | The password field is able to be filled up and only small black dots are seen | Pass | The good thing is that the password is hidden even as it is being typed out unlike some other sites where you can still see the characters as they are typed.
TC-2.2.6.3 | Press the "Sign In" button | nil | The user should get prompted to fill in the blank email field. | The user gets prompted to fill in the blank email field with an alert that appears | Pass | The alert appearing below the email field makes does a good job of catching the user eye and informing them to fill in the email field, its more intuitive than having a pop up alert at the top of the website

## TC-2.2.7
Project Name : | Recommender System based on collaborative filtering
Test CaseID : | TC-2.2.7
Test Case Description : | Try Individual login in with correct email and empty password field
Created by : | Muhamad Amir Akmal
Remarks: | Already at RECS website Login page
Pre-Condition : | Already have an Individual account created
Test Step | Test Step Description | Test Data | Expected Results | Actual Result | Pass/Fail | Remarks
TC-2.2.7.1 | Enter the correct email address of a registered Individual user account | Email = muhamad.amir.akmal@gmail.com | The email field is able to fill up properly with no issues, dispalying entered email address | The email field is able to be filled and displays "muhamad.amir.akmal@gmail.com" | Pass
TC-2.2.7.2 | Leave the password field blank | nil | At this stage nothing should happen as the "Sign In" button has not been clicked, password field remains empty | The password field is still blank | Pass | The good thing is that the password is hidden even as it is being typed out unlike some other sites where you can still see the characters as they are typed.
TC-2.2.7.3 | Press the "Sign In" button | nil | The login page should not authorize the login nor redirect to 2FA page. Either it prompts user to input password cause its empty or treat it like an invalid login and display generic general message. | The page remained on the Login page and prompts user that the password field has to be filled with an alert appearing just under the password field upon clicking the "Sign In" button | Pass | I think its good that it was done using an alert under the password field rather than treating it like an invalid login with error message as the user didn’t fill out the password field so an alert used to remind the user is good.

## TC-2.2.8
Project Name : | Recommender System based on collaborative filtering
Test CaseID : | TC-2.2.8
Test Case Description : | Try to bypass 2FA verification for Individual login by trying to enter without the verification code
Created by : | Muhamad Amir Akmal
Remarks: | Nil
Pre-Condition : | Already login in using Individual user account
Test Step | Test Step Description | Test Data | Expected Results | Actual Result | Pass/Fail | Remarks
TC-2.2.8.1 | Upon landing on the 2FA verification page, leave the 2FA code field blank | Nil | The 2FA field remains blank as there is no input in it | Since user never enter anything the field is still blank | Pass | nil
TC-2.2.8.2 | Press the "Verify" button | Nil | 2FA verification page shouldn’t verify user nor redirect them into the Individual user's home page | User remains on the 2FA verification page and does not get redirected to the Individual user's home page | Pass | It would be nice to have an alert prompt to fill up the 2FA verification code since it is blank when clicking on the "Verify" button

## TC-2.2.9
Project Name : | Recommender System based on collaborative filtering
Test CaseID : | TC-2.2.9
Test Case Description : | Enter correct 2FA code sent by RECS site for Individual login
Created by : | Muhamad Amir Akmal
Remarks: | Nil
Pre-Condition : | Already login in using Individual user account
Test Step | Test Step Description | Test Data | Expected Results | Actual Result | Pass/Fail | Remarks
TC-2.2.9.1 | Enter the 2FA code sent to the Individual user registered email by the RECS site | 2FA code received = 286812 | The 2FA code input field should fill up with no errors, there should not be any more than one digit in each input field. | Each input field only accepted one digit, and there was no errors/bugs in the input process | Pass | nil
TC-2.2.9.2 | Press the "Verify" button | Nil | The user should be verified and authenticated, the page will redirect the user to the Individual user's home page | RECS verifies and authenticates the user, redirecting them to the Individual user's home page | Pass | It would be nice to have an alert prompt to fill up the 2FA verification code since it is blank when clicking on the "Verify" button

## TC-2.2.10
Project Name : | Recommender System based on collaborative filtering
Test CaseID : | TC-2.2.10
Test Case Description : | Enter incorrect 2FA Code for Individual login
Created by : | Muhamad Amir Akmal
Remarks: | Nil
Pre-Condition : | Already login in using Individual user account
Test Step | Test Step Description | Test Data | Expected Results | Actual Result | Pass/Fail | Remarks
TC-2.2.10.1 | Enter any incorrect code for 2FA verification, to check and see if RECS properly checks the 2FA codes and prevents any wrongful verification/authentication | 2FA code received = 603434, 2FA code entered = 456323 | The 2FA code input field should fill up with no errors, there should not be any more than one digit in each input field. | Each input field only accepted one digit, and there was no errors/bugs in the input process | Pass | Nil
TC-2.2.10.2 | Press the "Verify" button | Nil | 2FA verification page shouldn’t verify user nor redirect them into the Individual user's home page, there should be error message to inform them of invalid verification | User remains on the 2FA verification page and does not get redirected to the Individual user's home page. All the 2FA code digit input field gets cleared. | Pass | An error message saying "invalid verification" or "unable to verify" in the event the user entered the digits wrongly, so that the user will know why the havent been verified and redirected.

## TC-2.2.11
Project Name : | Recommender System based on collaborative filtering
Test CaseID : | TC-2.2.11
Test Case Description : | Enter partial 2FA Code for Individual login
Created by : | Muhamad Amir Akmal
Remarks: | Nil
Pre-Condition : | Already login in using Individual user account
Test Step | Test Step Description | Test Data | Expected Results | Actual Result | Pass/Fail | Remarks
TC-2.2.11.1 | Enter only part of the 2FA verification code received via email, to check and see if RECS does proper checks on 2FA verification and prevents any wrongful verification/authentication | 2FA code received = 266962, 2FA code entered = 266 | The 2FA code input field should fill up with no errors, there should not be any more than one digit in each input field. | Each input field only accepted one digit, and there was no errors/bugs in the input process | Pass | Nil
TC-2.2.11.2 | Press the "Verify" button | Nil | 2FA verification page shouldn’t verify user nor redirect them into the Individual user's home page, there should be error message to inform them of invalid verification | User remains on the 2FA verification page and does not get redirected to the Individual user's home page. All the 2FA code digit input field gets cleared. | Pass | An error message saying "invalid verification" or "unable to verify" in the event the user entered the digits wrongly, so that the user will know why the havent been verified and redirected.

## TC-2.2.12
Project Name : | Recommender System based on collaborative filtering
Test CaseID : | TC-2.2.12
Test Case Description : | Click on "RECS" on top left of the 2FA verification page for Individual login with empty 2FA code field
Created by : | Muhamad Amir Akmal
Remarks: | Nil
Pre-Condition : | Already login in using Individual user account
Test Step | Test Step Description | Test Data | Expected Results | Actual Result | Pass/Fail | Remarks
TC-2.2.12.1 | Upon landing on the 2FA verification page, leave the 2FA code field blank | Nil | The 2FA field remains blank as there is no input in it | Since user never enter anything the field is still blank | Pass | nil
TC-2.2.12.2 | Press the "RECS" on the top left to check and make sure that the 2FA verification does not get bypass due to some bug/error and won't redirect into the Individual user's home page | Nil | The page does not redirect to the Individual user home page but rather the main landing page since the "RECS" is suppose to be a hyperlink button that takes user to the main page | User is redirected to the main landing page. User does not bypass the 2FA verification to their Individual user home page. | Pass | nil

## TC-2.2.13
Project Name : | Recommender System based on collaborative filtering
Test CaseID : | TC-2.2.13
Test Case Description : | Click on "RECS" on top left of the 2FA verification page for Individual login after entering 2FA code
Created by : | Muhamad Amir Akmal
Remarks: | Nil
Pre-Condition : | Already login in using Individual user account
Test Step | Test Step Description | Test Data | Expected Results | Actual Result | Pass/Fail | Remarks
TC-2.2.13.1 | Enter the 2FA code received via registered email for Individual user account verification | 2FA code received = 441636 | The 2FA field remains blank as there is no input in it | Since user never enter anything the field is still blank | Pass | nil
TC-2.2.13.2 | Press the "RECS" on the top left to check and make sure that the 2FA verification does not get bypass due to some bug/error and won't redirect into the Individual user's home page even if the 2FA code has been entered | Nil | The page should be redirected to the main landing page instead of bypassing 2FA into the Individual user's home page | User is redirected to the main landing page. User does not bypass the 2FA verification to their Individual user home page. | Pass

## TC-2.3.1
Project Name : | Recommender System based on collaborative filtering
Test CaseID : | TC-2.3.1
Test Case Description : | Login using correct email and password for Organization
Created by : | Muhamad Amir Akmal
Remarks: | Already at RECS Login page
Pre-Condition : | Already have an Organization user account created
Test Step | Test Step Description | Test Data | Expected Results | Actual Result | Pass/Fail | Remarks | Screenshot if fail
TC-2.3.1.1 | Enter the correct email address of registered Organization user account | Email = aqmal1199@gmail.com | The email field is able to fill up properly with no issues, dispalying entered email address | The email field is able to be filled and displays " aqmal1199@gmail.com" | Pass
TC-2.3.1.2 | Enter the correct password of registered Organization user account | Password = P@ssw0rd | The password field is able to fill up properly with no issues and the password should not be visible to user | The password field is able to be filled up and only small black dots are seen, the typed password cannot be seen | Pass | while typing each character, the characters are hidden which is good as it doesn’t allow onlookers to see the password as user is typing on screen
TC-2.3.1.3 | Press the "Sign In" button | nil | User should be redirected to 2FA verification page | The login page redirects to a verification page asking for 6 digit code sent to user as a form of 2FA verification | Pass

## TC-2.3.2
Project Name : | Recommender System based on collaborative filtering
Test CaseID : | TC-2.3.2
Test Case Description : | Login using incorrect email and correct password for Organization
Created by : | Muhamad Amir Akmal
Remarks: | Already at RECS website Login page
Pre-Condition : | Already have an Organization user account created
Test Step | Test Step Description | Test Data | Expected Results | Actual Result | Pass/Fail | Remarks | Screenshot if fail
TC-2.3.2.1 | Enter an incorrect email address | Email = orgtesting@gmail.com | The email field should still be able to fill up properly with no issues, dispalying incorrect email address | The email field is able to be filled and displays "orgtesting@gmail.com" | Pass
TC-2.3.2.2 | Enter the correct password of registered Organization user account | Password = P@ssw0rd | The password field is able to fill up properly with no issues and the password should not be visible to user | The password field is able to be filled up and only small black dots are seen | Pass | while typing each character, the characters are hidden which is good as it doesn’t allow onlookers to see the password as user is typing on screen
TC-2.3.2.3 | Press the "Sign In" button | nil | Remain on login page and there should be an invalid login message displayed | The page still remains on the login page, there is "Invalid login details" message in red. Email and password fields also got cleared | Pass | From user standpoint the red error message helps draw the user attention letting them know why they can't log in. From security standpoint generic error message and clearing of both input fields are good as it makes it harder for attackers find out which credential is right/wrong.

## TC-2.3.3
Project Name : | Recommender System based on collaborative filtering
Test CaseID : | TC-2.3.3
Test Case Description : | Login using correct email and incorrect password for Organization
Created by : | Muhamad Amir Akmal
Remarks: | Already at RECS website Login page
Pre-Condition : | Already have an Organization user account created
Test Step | Test Step Description | Test Data | Expected Results | Actual Result | Pass/Fail | Remarks | Screenshot if fail
TC-2.3.3.1 | Entering the correct Email a registered Organization account | Email = aqmal1199@gmail.com | The email field is able to fill up properly with no issues, dispalying entered email address | The email field is able to be filled and displays "aqmal1199@gmail.com" | Pass
TC-2.3.3.2 | Enter an incorrect password | Password = pwdpwd | The password field is should still be able to fill up properly with no issues and the incorrect password should not be visible to user | The password field is able to be filled up and only small black dots are seen, incorrect password typed is not seen | Pass
TC-2.3.3.3 | Press the "Sign In" button | nil | Remain on login page and there should be an invalid login message displayed | The page remained the same, the email and password field were cleared and there is "Invalid login details" message in red | Pass | Error in red is good as it catches the user's eyes and informs them of the login error. From a security standpoint it is good that the error message is generic and the input fields are also cleared so as to not let attackers know which entered credential is right/wrong.

## TC-2.3.4
Project Name : | Recommender System based on collaborative filtering
Test CaseID : | TC-2.3.4
Test Case Description : | Try Organization login in with the correct password but the alphabets in different Caps
Created by : | Muhamad Amir Akmal
Remarks: | Already at RECS Login page
Pre-Condition : | Already have an Organization account created
Test Step | Test Step Description | Test Data | Expected Results | Actual Result | Pass/Fail | Remarks | Screenshot if fail
TC-2.3.4.1 | Enter the correct email address of registered Organization user account | Email = aqmal1199@gmail.com | The email field is able to fill up properly with no issues, dispalying entered email address | The email field is able to be filled and displays "aqmal1199@gmail.com" | Pass
TC-2.3.4.2 | Enter the correct password of registered Organization user account except the alphabets in different caps, to test if website authorizes login when it shouldn’t | Password = P@ssw0rd | The password field is able to fill up properly with no issues and the password should not be visible to user | The password field is able to be filled up and only small black dots are seen | Pass | The good thing is that the password is hidden even as it is being typed out unlike some other sites where you can still see the characters as they are typed.
TC-2.3.4.3 | Press the "Sign In" button | nil | The website should not authenticate and redirect to the 2FA verification page as the password is in the wrong caps | The website remains on the login page, there is "Invalid login details" message in red. Email and password fields also got cleared . | Pass | Site is able to recognize that same password but in different caps for the alphabet characters does not equal to the same registered password and does not authorize login, which is good and helps limit breaching vectors for the login

## TC-2.3.5
Project Name : | Recommender System based on collaborative filtering
Test CaseID : | TC-2.3.5
Test Case Description : | Try Organization login with email in caps
Created by : | Muhamad Amir Akmal
Remarks: | Already at RECS Login page
Pre-Condition : | Already have an Organization account created
Test Step | Test Step Description | Test Data | Expected Results | Actual Result | Pass/Fail | Remarks
TC-2.3.5.1 | Enter the correct email address of registered Organization user account just in different caps | Email = AQmal1199@gmail.com | The email field is able to fill up properly with no issues, dispalying entered email address | The email field is able to be filled and displays "AQmal1199@gmail.com " | Pass
TC-2.3.5.2 | Enter the correct password of registered Organization user account | Password = P@ssw0rd | The password field is able to fill up properly with no issues and the password should not be visible to user | The password field is able to be filled up and only small black dots are seen | Pass | The good thing is that the password is hidden even as it is being typed out unlike some other sites where you can still see the characters as they are typed.
TC-2.3.5.3 | Press the "Sign In" button | nil | The website should authorize the Organization user login and redirect to 2FA verification page as email is not caps sensitive | The website authorizes login and redirects as per usual to the 2FA verification page | Pass

## TC-2.3.6
Project Name : | Recommender System based on collaborative filtering
Test CaseID : | TC-2.3.6
Test Case Description : | Try Organization login in with empty email field and correct password
Created by : | Muhamad Amir Akmal
Remarks: | Already at RECS website Login page
Pre-Condition : | Already have an Organization account created
Test Step | Test Step Description | Test Data | Expected Results | Actual Result | Pass/Fail | Remarks
TC-2.3.6.1 | Leave the email field blank | nil | Nothing should happen as the "Sign In" button has not been clicked, email field remains empty | Nothing happens since it was left blank | Pass
TC-2.3.6.2 | Enter the correct password of registered Organization user account | Password = P@ssw0rd | The password field is able to fill up properly with no issues and the password should not be visible to user | The password field is able to be filled up and only small black dots are seen | Pass | The good thing is that the password is hidden even as it is being typed out unlike some other sites where you can still see the characters as they are typed.
TC-2.3.6.3 | Press the "Sign In" button | nil | The user should get prompted to fill in the blank email field. | The user gets prompted to fill in the blank email field with an alert that appears | Pass | The alert appearing below the email field makes does a good job of catching the user eye and informing them to fill in the email field, its more intuitive than having a pop up alert at the top of the website

## TC-2.3.7
Project Name : | Recommender System based on collaborative filtering
Test CaseID : | TC-2.3.7
Test Case Description : | Try Organization login in with correct email and empty password field
Created by : | Muhamad Amir Akmal
Remarks: | Already at RECS website Login page
Pre-Condition : | Already have an Organization account created
Test Step | Test Step Description | Test Data | Expected Results | Actual Result | Pass/Fail | Remarks
TC-2.3.7.1 | Enter the correct email address of a registered Organization user account | Email = aqmal1199@gmail.com | The email field is able to fill up properly with no issues, dispalying entered email address | The email field is able to be filled and displays "aqmal1199@gmail.com" | Pass
TC-2.3.7.2 | Leave the password field blank | nil | At this stage nothing should happen as the "Sign In" button has not been clicked, password field remains empty | The password field is still blank | Pass | The good thing is that the password is hidden even as it is being typed out unlike some other sites where you can still see the characters as they are typed.
TC-2.3.7.3 | Press the "Sign In" button | nil | The login page should not authorize the login nor redirect to 2FA page. Either it prompts user to input password cause its empty or treat it like an invalid login and display generic general message. | The page remained on the Login page and prompts user that the password field has to be filled with an alert appearing just under the password field upon clicking the "Sign In" button | Pass | I think its good that it was done using an alert under the password field rather than treating it like an invalid login with error message as the user didn’t fill out the password field so an alert used to remind the user is good.

## TC-2.3.8
Project Name : | Recommender System based on collaborative filtering
Test CaseID : | TC-2.3.8
Test Case Description : | Try to bypass 2FA verification for Organization login by trying to enter without the verification code
Created by : | Muhamad Amir Akmal
Remarks: | Nil
Pre-Condition : | Already login in using Organization user account
Test Step | Test Step Description | Test Data | Expected Results | Actual Result | Pass/Fail | Remarks
TC-2.3.8.1 | Upon landing on the 2FA verification page, leave the 2FA code field blank | Nil | The 2FA field remains blank as there is no input in it | Since user never enter anything the field is still blank | Pass | nil
TC-2.3.8.2 | Press the "Verify" button | Nil | 2FA verification page shouldn’t verify user nor redirect them into the Organization user's home page | User remains on the 2FA verification page and does not get redirected to the Organization user's home page | Pass | It would be nice to have an alert prompt to fill up the 2FA verification code since it is blank when clicking on the "Verify" button

## TC-2.3.9
Project Name : | Recommender System based on collaborative filtering
Test CaseID : | TC-2.3.9
Test Case Description : | Enter correct 2FA code sent by RECS site for Organization login
Created by : | Muhamad Amir Akmal
Remarks: | Nil
Pre-Condition : | Already login in using Organization user account
Test Step | Test Step Description | Test Data | Expected Results | Actual Result | Pass/Fail | Remarks
TC-2.3.9.1 | Enter the 2FA code sent to the Organization user registered email by the RECS site | 2FA code received = 330696 | The 2FA code input field should fill up with no errors, there should not be any more than one digit in each input field. | Each input field only accepted one digit, and there was no errors/bugs in the input process | Pass | nil
TC-2.3.9.2 | Press the "Verify" button | Nil | The user should be verified and authenticated, the page will redirect the user to the Organization user's home page | RECS verifies and authenticates the user, redirecting them to the Organization user's home page | Pass | It would be nice to have an alert prompt to fill up the 2FA verification code since it is blank when clicking on the "Verify" button

## TC-2.3.10
Project Name : | Recommender System based on collaborative filtering
Test CaseID : | TC-2.3.10
Test Case Description : | Enter incorrect 2FA Code for Organization login
Created by : | Muhamad Amir Akmal
Remarks: | Nil
Pre-Condition : | Already login in using Organization user account
Test Step | Test Step Description | Test Data | Expected Results | Actual Result | Pass/Fail | Remarks
TC-2.3.10.1 | Enter any incorrect code for 2FA verification, to check and see if RECS properly checks the 2FA codes and prevents any wrongful verification/authentication | 2FA code received = 907251, 2FA code entered = 223541 | The 2FA code input field should fill up with no errors, there should not be any more than one digit in each input field. | Each input field only accepted one digit, and there was no errors/bugs in the input process | Pass | Nil
TC-2.3.10.2 | Press the "Verify" button | Nil | 2FA verification page shouldn’t verify user nor redirect them into the Organization user's home page, there should be error message to inform them of invalid verification | User remains on the 2FA verification page and does not get redirected to the Organization user's home page. All the 2FA code digit input field gets cleared. | Pass | Informed Rui Hao that an error message should be added for when user enters wrong 2FA code. An error message saying "invalid verification" or "unable to verify" in the event the user entered the digits wrongly, so that the user will know why the havent been verified and redirected.

## TC-2.3.11
Project Name : | Recommender System based on collaborative filtering
Test CaseID : | TC-2.3.11
Test Case Description : | Enter partial 2FA Code for Organization login
Created by : | Muhamad Amir Akmal
Remarks: | Nil
Pre-Condition : | Already login in using Organization user account
Test Step | Test Step Description | Test Data | Expected Results | Actual Result | Pass/Fail | Remarks
TC-2.3.11.1 | Enter only part of the 2FA verification code received via email, to check and see if RECS does proper checks on 2FA verification and prevents any wrongful verification/authentication | 2FA code received = 344686, 2FA code entered = 686 | The 2FA code input field should fill up with no errors, there should not be any more than one digit in each input field. | Each input field only accepted one digit, and there was no errors/bugs in the input process | Pass | Nil
TC-2.3.11.2 | Press the "Verify" button | Nil | 2FA verification page shouldn’t verify user nor redirect them into the Organization user's home page, there should be error message to inform them of invalid verification | User remains on the 2FA verification page and does not get redirected to the Organization user's home page. All the 2FA code digit input field gets cleared. | Pass | An error message saying "invalid verification" or "unable to verify" in the event the user entered the digits wrongly, so that the user will know why the havent been verified and redirected.

## TC-2.3.12
Project Name : | Recommender System based on collaborative filtering
Test CaseID : | TC-2.3.12
Test Case Description : | Click on "RECS" on top left of the 2FA verification page for Organization login with empty 2FA code field
Created by : | Muhamad Amir Akmal
Remarks: | Nil
Pre-Condition : | Already login in using Organization user account
Test Step | Test Step Description | Test Data | Expected Results | Actual Result | Pass/Fail | Remarks
TC-2.3.12.1 | Upon landing on the 2FA verification page, leave the 2FA code field blank | Nil | The 2FA field remains blank as there is no input in it | Since user never enter anything the field is still blank | Pass | nil
TC-2.3.12.2 | Press the "RECS" on the top left to check and make sure that the 2FA verification does not get bypass due to some bug/error and won't redirect into the Organization user's home page | Nil | The page does not redirect to the Organization user home page but rather the main landing page since the "RECS" is suppose to be a hyperlink button that takes user to the main page | User is redirected to the main landing page. User does not bypass the 2FA verification to their Organization user home page. | Pass | nil

## TC-2.3.13
Project Name : | Recommender System based on collaborative filtering
Test CaseID : | TC-2.3.13
Test Case Description : | Click on "RECS" on top left of the 2FA verification page for Organization login after entering 2FA code
Created by : | Muhamad Amir Akmal
Remarks: | Nil
Pre-Condition : | Already login in using Organization user account
Test Step | Test Step Description | Test Data | Expected Results | Actual Result | Pass/Fail | Remarks
TC-2.3.13.1 | Enter the 2FA code received via registered email for Organization user account verification | 2FA code received = 204361 | The 2FA field remains blank as there is no input in it | Since user never enter anything the field is still blank | Pass | nil
TC-2.3.13.2 | Press the "RECS" on the top left to check and make sure that the 2FA verification does not get bypass due to some bug/error and won't redirect into the Organization user's home page even if the 2FA code has been entered | Nil | The page should be redirected to the main landing page instead of bypassing 2FA into the Organization user's home page | User is redirected to the main landing page. User does not bypass the 2FA verification to their Organization user home page. | Pass

## TC-2.4.1
Project Name : | Recommender System based on collaborative filtering
Test CaseID : | TC-2.4.1
Test Case Description : | Login using correct email and password for Admin
Created by : | Muhamad Amir Akmal
Remarks: | Already at RECS Login page
Pre-Condition : | Already have an Admin account created
Test Step | Test Step Description | Test Data | Expected Results | Actual Result | Pass/Fail | Remarks
TC-2.4.1.1 | Enter the correct email address of registered Admin user account | Email = md_amir_akmal@yahoo.com.sg | The email field is able to fill up properly with no issues, dispalying entered email address | The email field is able to be filled and displays "md_amir_akmal@yahoo.com.sg" | Pass
TC-2.4.1.2 | Enter the correct password of registered Admin user account | Password = Fyp123456! | The password field is able to fill up properly with no issues and the password should not be visible to user | The password field is able to be filled up and only small black dots are seen | Pass | The good thing is that the password is hidden even as it is being typed out unlike some other sites where you can still see the characters as they are typed.
TC-2.4.1.3 | Press the "Sign In" button | nil | User should be redirected to 2FA verification page | The login page redirects to a verification page asking for 6 digit code sent to user as a form of 2FA verification | Pass

## TC-2.4.2
Project Name : | Recommender System based on collaborative filtering
Test CaseID : | TC-2.3.2
Test Case Description : | Login using incorrect email and correct password for Admin
Created by : | Muhamad Amir Akmal
Remarks: | Already at RECS website Login page
Pre-Condition : | Already have an Admin user account created
Test Step | Test Step Description | Test Data | Expected Results | Actual Result | Pass/Fail | Remarks
TC-2.3.2.1 | Enter an incorrect email address | Email = testadmin@yahoo.com.sg | The email field should still be able to fill up properly with no issues, dispalying incorrect email address | The email field is able to be filled and displays "testadmin@yahoo.com.sg " | Pass
TC-2.3.2.2 | Enter the correct password of registered Admin user account | Password = Fyp123456! | The password field is able to fill up properly with no issues and the password should not be visible to user | The password field is able to be filled up and only small black dots are seen | Pass | while typing each character, the characters are hidden which is good as it doesn’t allow onlookers to see the password as user is typing on screen
TC-2.3.2.3 | Press the "Sign In" button | nil | Remain on login page and there should be an invalid login message displayed | The page still remains on the login page, there is "Invalid login details" message in red. Email and password fields also got cleared | Pass | From user standpoint the red error message helps draw the user attention letting them know why they can't log in. From security standpoint generic error message and clearing of both input fields are good as it makes it harder for attackers find out which credential is right/wrong.

## TC-2.4.3
Project Name : | Recommender System based on collaborative filtering
Test CaseID : | TC-2.3.3
Test Case Description : | Login using correct email and incorrect password for Admin
Created by : | Muhamad Amir Akmal
Remarks: | Already at RECS website Login page
Pre-Condition : | Already have an Admin user account created
Test Step | Test Step Description | Test Data | Expected Results | Actual Result | Pass/Fail | Remarks
TC-2.3.3.1 | Entering the correct Email a registered Admin account | Email = md_amir_akmal@yahoo.com.sg | The email field is able to fill up properly with no issues, dispalying entered email address | The email field is able to be filled and displays "md_amir_akmal@yahoo.com.sg" | Pass
TC-2.3.3.2 | Enter an incorrect password | Password = 123fpy@ | The password field is should still be able to fill up properly with no issues and the incorrect password should not be visible to user | The password field is able to be filled up and only small black dots are seen, incorrect password typed is not seen | Pass | security wise its good that while typing each character, the characters are hidden which is good as it doesn’t allow onlookers to see the password as user is typing on screen
TC-2.3.3.3 | Press the "Sign In" button | nil | Remain on login page and there should be an invalid login message displayed | The page remained the same, the email and password field were cleared and there is "Invalid login details" message in red | Pass | From user standpoint the red error message helps draw the user attention letting them know why they can't log in. From security standpoint generic error message and clearing of both input fields are good as it makes it harder for attackers find out which credential is right/wrong.

## TC-2.4.4
Project Name : | Recommender System based on collaborative filtering
Test CaseID : | TC-2.4.4
Test Case Description : | Try Admin login in with the correct password but the alphabets in different Caps
Created by : | Muhamad Amir Akmal
Remarks: | Already at RECS Login page
Pre-Condition : | Already have an Admin account created
Test Step | Test Step Description | Test Data | Expected Results | Actual Result | Pass/Fail | Remarks
TC-2.4.4.1 | Enter the correct email address of registered Admin user account | Email = md_amir_akmal@yahoo.com.sg | The email field is able to fill up properly with no issues, dispalying entered email address | The email field is able to be filled and displays "md_amir_akmal@yahoo.com.sg " | Pass
TC-2.4.4.2 | Enter the correct password of registered Admin user account except the alphabets in different caps, to test if website authorizes login when it shouldn’t | Password = fYP123456! | The password field is able to fill up properly with no issues and the password should not be visible to user | The password field is able to be filled up and only small black dots are seen | Pass | The good thing is that the password is hidden even as it is being typed out unlike some other sites where you can still see the characters as they are typed.
TC-2.4.4.3 | Press the "Sign In" button | nil | The website should not authenticate and redirect to the 2FA verification page as the password is in the wrong caps | The website remains on the login page, there is "Invalid login details" message in red. Email and password fields also got cleared . | Pass | Site is able to recognize that same password but in different caps for the alphabet characters does not equal to the same registered password and does not authorize login, which is good and helps limit breaching vectors for the login

## TC-2.4.5
Project Name : | Recommender System based on collaborative filtering
Test CaseID : | TC-2.4.5
Test Case Description : | Try Admin login with email in caps
Created by : | Muhamad Amir Akmal
Remarks: | Already at RECS Login page
Pre-Condition : | Already have an Admin account created
Test Step | Test Step Description | Test Data | Expected Results | Actual Result | Pass/Fail | Remarks
TC-2.4.5.1 | Enter the correct email address of registered Admin user account just in different caps | Email = MD_amir_Akmal@yahoo.com.sg | The email field is able to fill up properly with no issues, dispalying entered email address | The email field is able to be filled and displays "MD_amir_Akmal@yahoo.com.sg " | Pass
TC-2.4.5.2 | Enter the correct password of registered Admin user account | Password = Fyp123456! | The password field is able to fill up properly with no issues and the password should not be visible to user | The password field is able to be filled up and only small black dots are seen | Pass | The good thing is that the password is hidden even as it is being typed out unlike some other sites where you can still see the characters as they are typed.
TC-2.4.5.3 | Press the "Sign In" button | nil | The website should authorize the Admin user login and redirect to 2FA verification page as email is not caps sensitive | The website authorizes login and redirects as per usual to the 2FA verification page | Pass

## TC-2.4.6
Project Name : | Recommender System based on collaborative filtering
Test CaseID : | TC-2.4.6
Test Case Description : | Try Admin login in with empty email field and correct password
Created by : | Muhamad Amir Akmal
Remarks: | Already at RECS website Login page
Pre-Condition : | Already have an Admin account created
Test Step | Test Step Description | Test Data | Expected Results | Actual Result | Pass/Fail | Remarks
TC-2.4.6.1 | Leave the email field blank | nil | Nothing should happen as the "Sign In" button has not been clicked, email field remains empty | Nothing happens since it was left blank | Pass
TC-2.4.6.2 | Enter the correct password of registered Admin user account | Password = Fyp123456! | The password field is able to fill up properly with no issues and the password should not be visible to user | The password field is able to be filled up and only small black dots are seen | Pass | The good thing is that the password is hidden even as it is being typed out unlike some other sites where you can still see the characters as they are typed.
TC-2.4.6.3 | Press the "Sign In" button | nil | The user should get prompted to fill in the blank email field. | The user gets prompted to fill in the blank email field with an alert that appears | Pass | The alert appearing below the email field makes does a good job of catching the user eye and informing them to fill in the email field, its more intuitive than having a pop up alert at the top of the website

## TC-2.4.7
Project Name : | Recommender System based on collaborative filtering
Test CaseID : | TC-2.4.7
Test Case Description : | Try Admin login in with correct email and empty password field
Created by : | Muhamad Amir Akmal
Remarks: | Already at RECS website Login page
Pre-Condition : | Already have an Admin account created
Test Step | Test Step Description | Test Data | Expected Results | Actual Result | Pass/Fail | Remarks
TC-2.4.7.1 | Enter the correct email address of a registered Admin user account | Email = md_amir_akmal@yahoo.com.sg | The email field is able to fill up properly with no issues, dispalying entered email address | The email field is able to be filled and displays "md_amir_akmal@yahoo.com.sg" | Pass
TC-2.4.7.2 | Leave the password field blank | nil | At this stage nothing should happen as the "Sign In" button has not been clicked, password field remains empty | The password field is still blank | Pass | The good thing is that the password is hidden even as it is being typed out unlike some other sites where you can still see the characters as they are typed.
TC-2.4.7.3 | Press the "Sign In" button | nil | The login page should not authorize the login nor redirect to 2FA page. Either it prompts user to input password cause its empty or treat it like an invalid login and display generic general message. | The page remained on the Login page and prompts user that the password field has to be filled with an alert appearing just under the password field upon clicking the "Sign In" button | Pass | I think its good that it was done using an alert under the password field rather than treating it like an invalid login with error message as the user didn’t fill out the password field so an alert used to remind the user is good.

## TC-2.4.8
Project Name : | Recommender System based on collaborative filtering
Test CaseID : | TC-2.4.8
Test Case Description : | Try to bypass 2FA verification for Admin login by trying to enter without the verification code
Created by : | Muhamad Amir Akmal
Remarks: | Nil
Pre-Condition : | Already login in using Admin user account
Test Step | Test Step Description | Test Data | Expected Results | Actual Result | Pass/Fail | Remarks
TC-2.4.8.1 | Upon landing on the 2FA verification page, leave the 2FA code field blank | Nil | The 2FA field remains blank as there is no input in it | Since user never enter anything the field is still blank | Pass | nil
TC-2.4.8.2 | Press the "Verify" button | Nil | 2FA verification page shouldn’t verify user nor redirect them into the Admin user's home pagehome page | User remains on the 2FA verification page and does not get redirected to the Admin user's home page home page | Pass | It would be nice to have an alert prompt to fill up the 2FA verification code since it is blank when clicking on the "Verify" button

## TC-2.4.9
Project Name : | Recommender System based on collaborative filtering
Test CaseID : | TC-2.4.9
Test Case Description : | Enter correct 2FA code sent by RECS site for Admin login
Created by : | Muhamad Amir Akmal
Remarks: | Nil
Pre-Condition : | Already login in using Admin user account
Test Step | Test Step Description | Test Data | Expected Results | Actual Result | Pass/Fail | Remarks
TC-2.4.9.1 | Enter the 2FA code sent to the Admin user registered email by the RECS site | 2FA code received = 852822 | The 2FA code input field should fill up with no errors, there should not be any more than one digit in each input field. | Each input field only accepted one digit, and there was no errors/bugs in the input process | Pass | nil
TC-2.4.9.2 | Press the "Verify" button | Nil | The user should be verified and authenticated, the page will redirect the user to the Admin user's home page | RECS verifies and authenticates the user, redirecting them to the Admin user's home page | Pass | It would be nice to have an alert prompt to fill up the 2FA verification code since it is blank when clicking on the "Verify" button

## TC-2.4.10
Project Name : | Recommender System based on collaborative filtering
Test CaseID : | TC-2.4.10
Test Case Description : | Enter incorrect 2FA Code for Admin login
Created by : | Muhamad Amir Akmal
Remarks: | Nil
Pre-Condition : | Already login in using Admin user account
Test Step | Test Step Description | Test Data | Expected Results | Actual Result | Pass/Fail | Remarks
TC-2.4.10.1 | Enter any incorrect code for 2FA verification, to check and see if RECS properly checks the 2FA codes and prevents any wrongful verification/authentication | 2FA code received = 602483, 2FA code entered = 225621 | The 2FA code input field should fill up with no errors, there should not be any more than one digit in each input field. | Each input field only accepted one digit, and there was no errors/bugs in the input process | Pass | Nil
TC-2.4.10.2 | Press the "Verify" button | Nil | 2FA verification page shouldn’t verify user nor redirect them into the Admin user's home page, there should be error message to inform them of invalid verification | User remains on the 2FA verification page and does not get redirected to the Admin user's home page. All the 2FA code digit input field gets cleared. | Pass | Informed Rui Hao that an error message should be added for when user enters wrong 2FA code. An error message saying "invalid verification" or "unable to verify" in the event the user entered the digits wrongly, so that the user will know why the havent been verified and redirected.

## TC-2.4.11
Project Name : | Recommender System based on collaborative filtering
Test CaseID : | TC-2.4.11
Test Case Description : | Enter partial 2FA Code for Admin login
Created by : | Muhamad Amir Akmal
Remarks: | Nil
Pre-Condition : | Already login in using Admin user account
Test Step | Test Step Description | Test Data | Expected Results | Actual Result | Pass/Fail | Remarks
TC-2.4.11.1 | Enter only part of the 2FA verification code received via email, to check and see if RECS does proper checks on 2FA verification and prevents any wrongful verification/authentication | 2FA code received = 267015, 2FA code entered = 701 | The 2FA code input field should fill up with no errors, there should not be any more than one digit in each input field. | Each input field only accepted one digit, and there was no errors/bugs in the input process | Pass | Nil
TC-2.4.11.2 | Press the "Verify" button | Nil | 2FA verification page shouldn’t verify user nor redirect them into the Admin user's home page, there should be error message to inform them of invalid verification | User remains on the 2FA verification page and does not get redirected to the Admin user's home page. All the 2FA code digit input field gets cleared. | Pass | An error message saying "invalid verification" or "unable to verify" in the event the user entered the digits wrongly, so that the user will know why the havent been verified and redirected.

## TC-2.4.12
Project Name : | Recommender System based on collaborative filtering
Test CaseID : | TC-2.4.12
Test Case Description : | Click on "RECS" on top left of the 2FA verification page for Admin login with empty 2FA code field
Created by : | Muhamad Amir Akmal
Remarks: | Nil
Pre-Condition : | Already login in using Admin user account
Test Step | Test Step Description | Test Data | Expected Results | Actual Result | Pass/Fail | Remarks
TC-2.4.12.1 | Upon landing on the 2FA verification page, leave the 2FA code field blank | Nil | The 2FA field remains blank as there is no input in it | Since user never enter anything the field is still blank | Pass | nil
TC-2.4.12.2 | Press the "RECS" on the top left to check and make sure that the 2FA verification does not get bypass due to some bug/error and won't redirect into the Admin user's home page | Nil | The page does not redirect to the Admin user home page but rather the main landing page since the "RECS" is suppose to be a hyperlink button that takes user to the main page | User is redirected to the main landing page. User does not bypass the 2FA verification to their Admin user home page. | Pass | nil

## TC-2.4.13
Project Name : | Recommender System based on collaborative filtering
Test CaseID : | TC-2.4.13
Test Case Description : | Click on "RECS" on top left of the 2FA verification page for Admin login after entering 2FA code
Created by : | Muhamad Amir Akmal
Remarks: | Nil
Pre-Condition : | Already login in using Admin user account
Test Step | Test Step Description | Test Data | Expected Results | Actual Result | Pass/Fail | Remarks
TC-2.4.13.1 | Enter the 2FA code received via registered email for Admin user account verification | 2FA code received = 155399 | The 2FA field remains blank as there is no input in it | Since user never enter anything the field is still blank | Pass | nil
TC-2.4.13.2 | Press the "RECS" on the top left to check and make sure that the 2FA verification does not get bypass due to some bug/error and won't redirect into the Admin user's home page even if the 2FA code has been entered | Nil | The page should be redirected to the main landing page instead of bypassing 2FA into the Admin user's home page | User is redirected to the main landing page. User does not bypass the 2FA verification to their Admin user home page. | Pass

## TC-2.5.1
Project Name : | Recommender System based on collaborative filtering
Test CaseID : | TC-2.5.1
Test Case Description : | Upon landing on the login page, multiple fast clicks on Sign In button
Created by : | Muhamad Amir Akmal
Remarks: | From main landing page of RECS website
Pre-Condition : | Using an already registered account
Test Step | Test Step Description | Test Data | Expected Results | Actual Result | Pass/Fail | Remarks | Screenshot if fail
TC-2.5.1.1 | Press on the "Login" button | Nil | Redirects to the Login page | The site is redirected to the Login page | Pass
TC-2.5.1.2 | Immediately spam clicks on the "Sign In" button | Nil | The page should remain on the Login page. The page should not break nor be redirected to 2FA page | The page remains on Login page, the page did not redirect nor break. The email field prompts user for input "Please fill out this field" | Pass

## TC-2.5.2
Project Name : | Recommender System based on collaborative filtering
Test CaseID : | TC-2.5.2
Test Case Description : | Upon landing on the login page, multiple fast clicks on Sign In button
Created by : | Muhamad Amir Akmal
Remarks: | From main landing page of RECS website
Pre-Condition : | Using an already registered account
Test Step | Test Step Description | Test Data | Expected Results | Actual Result | Pass/Fail | Remarks
TC-2.5.2.1 | Press on the "Login" button | Nil | Redirects to the Login page | The site is redirected to the Login page | Pass
TC-2.5.2.2 | Fill up the email field accordingly with any correct user credentials | Email: muhamad.amir.akmal@gmail.com | Email field should fill up accordingly and display the typed email | Email field fills up correctly, with no errors, displaying "muhamad.amir.akmal@gmail.com" | Pass
TC-2.5.2.3 | Fill up the password field accordingly with any correct user credentials | Password: pwd123 | Password field should be filled up without displaying the password in plain text. The password should be hidden | Password field does not display the typed password, hiding it by displaying small blackdots in place of each character | Pass
TC-2.5.2.4 | Spam multiple clicks on the "Sign In" button to check if somehow there is a bug that allows user to bypass 2FA verification | nil | The page should not break, and because the details are filled, the page should redirect to 2FA page as per normal and not bypass the 2FA verification | The page didn’t break and redirects to the 2FA verification page as per normal | Pass | The redirecting of the page takes slightly longer than if the "Sign In" button is clicked once

## TC-2.5.3
Project Name : | Recommender System based on collaborative filtering
Test CaseID : | TC-2.5.3
Test Case Description : | Click on "Forgot Password?"
Created by : | Muhamad Amir Akmal
Remarks:
Pre-Condition : | Already at login page
Test Step | Test Step Description | Test Data | Expected Results | Actual Result | Pass/Fail | Remarks
TC-2.5.3.1 | Click on "Forget Password" | Nil | User should be redirected to the Forget password page | The website redirects user to the forget password page where user can see RECS asking them to enter their email address | Pass | nil

## TC-2.5.4
Project Name : | Recommender System based on collaborative filtering
Test CaseID : | TC-2.5.4
Test Case Description : | On "Forget Password" page, click verify with empty email field
Created by : | Muhamad Amir Akmal
Remarks: | Already at RECS website Login page
Pre-Condition : | at the forgot password page
Test Step | Test Step Description | Test Data | Expected Results | Actual Result | Pass/Fail | Remarks
TC-2.5.4.1 | Leave the email field blank | nil | Nothing should happen as the "verify" button has not been clicked, email field remains empty | Nothing happens since it was left blank | Pass | nil
TC-2.5.4.2 | Click "Verify" | nil | There should be an alert prompting user to fill in their email | User can see an alert appear below the email field "Please fill out this field" | Pass | nil

## TC-2.5.5
Project Name : | Recommender System based on collaborative filtering
Test CaseID : | TC-2.5.5
Test Case Description : | On "Forget Password" page, enter incorrect email
Created by : | Muhamad Amir Akmal
Remarks: | Already at RECS website Login page
Pre-Condition : | at the forgot password page
Test Step | Test Step Description | Test Data | Expected Results | Actual Result | Pass/Fail | Remarks
TC-2.5.5.1 | Enter incorrect email of any type of user | email = testind@gmail.com | The email field should be able to fill up accordingly with no errors, | Email field reflects the entered input " testind@gmail.com" and there were no other errors | Pass | nil
TC-2.5.5.2 | Click "Verify" | nil | Since the email is a fake and there should be an error message that informs user that the email address is either wrong or cant be found | RECS returns an error message in red below the email field "Email address not found" | Pass | nil

## TC-2.5.6
Project Name : | Recommender System based on collaborative filtering
Test CaseID : | TC-2.5.6
Test Case Description : | On "Forget Password" page, click verify with empty email field
Created by : | Muhamad Amir Akmal
Remarks: | Already at RECS website Login page
Pre-Condition : | test using any of the registered user account created
Test Step | Test Step Description | Test Data | Expected Results | Actual Result | Pass/Fail | Remarks
TC-2.5.6.1 | Enter email address of a registered user | email = aqmal1199@gmail.com | The email field should be able to fill up accordingly with no errors, | Email field reflects the entered input " aqmal1199@gmail.com" and there were no other errors | Pass | nil
TC-2.5.6.2 | Click "Verify" | nil | Just like login/sing up to be secure RECS should sent a veriification code to confirm that it is indeed the user that is attempting to reset password | RECS redirects user to the page asking for verification code sent to the email before allowing user to reset password | Pass | nil

## TC-2.5.7
Project Name : | Recommender System based on collaborative filtering
Test CaseID : | TC-2.5.7
Test Case Description : | On verify email page, enter the verification code received
Created by : | Muhamad Amir Akmal
Remarks: | Already at RECS website Login page
Pre-Condition : | test using any of the registered user account created
Test Step | Test Step Description | Test Data | Expected Results | Actual Result | Pass/Fail | Remarks
TC-2.5.7.1 | Enter the verification code sent to the registered email that is requesting the password reset | code = 145009 | The digit code input fields should be able to fill up correctly | The verification code is successfully entered with no errors reflecting the code "145009" | Pass | nil
TC-2.5.7.2 | Click "Verify" | nil | RECS should now allow user to reset their password | RECS redirects user to a page where they ask user to enter password and "Re-enter" password for confirmation | Pass | nil

## TC-2.5.8
Project Name : | Recommender System based on collaborative filtering
Test CaseID : | TC-2.5.8
Test Case Description : | On "Forget Password" page, leave password field blank and try to update
Created by : | Muhamad Amir Akmal
Remarks: | Already at RECS website Login page
Pre-Condition : | at the forgot password page
Test Step | Test Step Description | Test Data | Expected Results | Actual Result | Pass/Fail | Remarks
TC-2.5.8.1 | Leave the password field blank | nil | Nothing should happen as the "update" button has not been clicked, password field remains empty | Nothing happens since it was left blank | Pass | nil
TC-2.5.8.2 | Click "update" | nil | There should be an alert prompting user to fill in their Password | User can see an alert appear below the Password field "Please fill out this field" | Pass | nil
TC-2.5.8.3 | enter a new password and leave re-enter password field blank | passsword= pwd2134 | The password field should be filled but the password should not be seen and the re-enter field has to be blank | Password field shows the password entered in small black dots and re-enter field is still blank | Pass | nil
TC-2.5.8.4 | Click "update" | nil | There should be an alert prompting user to fill in their Password in the "Re-enter" password field | User can see an alert appear below the"Re-enter" password field"Please fill out this field" | Pass | nil

## TC-2.5.9
Project Name : | Recommender System based on collaborative filtering
Test CaseID : | TC-2.5.9
Test Case Description : | On "Forget Password" page, enter different passwords into the two fields
Created by : | Muhamad Amir Akmal
Remarks: | Already at RECS website Login page
Pre-Condition : | at the forgot password page
Test Step | Test Step Description | Test Data | Expected Results | Actual Result | Pass/Fail | Remarks
TC-2.5.9.1 | Enter a new password | passsword= Pwd2!345 | The password field should be filled but the password should not be seen and the re-enter field should remainblank | Password field shows the password entered in small black dots and re-enter field is still blank | Pass | nil
TC-2.5.9.2 | enter a different password in re-enter password field | passsword= fypw345! | The re-enter password field should be filled but the password should not be seen | Re-enter password field shows the password entered in small black dots | Pass | nil
TC-2.5.9.3 | Click "update" | nil | There should be an alert prompting user their passwords don’t match | There is an error messsage in red below the Re-enter password field informing user "Password missmatch" | Pass | nil

## TC-2.5.10
Project Name : | Recommender System based on collaborative filtering
Test CaseID : | TC-2.5.10
Test Case Description : | On "Forget Password" page, entersame passwords but not in suggested format
Created by : | Muhamad Amir Akmal
Remarks: | the format is to have a minimum of 8 characters,with 1 of upper and lower case and numeric digit and special characters
Pre-Condition : | at the forgot password page
Test Step | Test Step Description | Test Data | Expected Results | Actual Result | Pass/Fail | Remarks
TC-2.5.10.1 | Enter a new password | passsword= testpwd12 | The password field should be filled but the password should not be seen and the re-enter field should remainblank | Password field shows the password entered in small black dots and re-enter field is still blank | Pass | nil
TC-2.5.10.2 | enter a different password in re-enter password field | passsword= testpwd12! | The re-enter password field should be filled but the password should not be seen | Re-enter password field shows the password entered in small black dots | Pass | nil
TC-2.5.10.3 | Click "update" | nil | There should be an alert prompting user to match the suggested format, this is due to ensure that the password is not easy to crack | There is an alert that pops up at informing user "Please match the requested format" | Pass | nil

## TC-2.5.11
Project Name : | Recommender System based on collaborative filtering
Test CaseID : | TC-2.5.11
Test Case Description : | On "Forget Password" page, enter correct new passwords
Created by : | Muhamad Amir Akmal
Remarks: | Already at RECS website Login page
Pre-Condition : | at the forgot password page
Test Step | Test Step Description | Test Data | Expected Results | Actual Result | Pass/Fail | Remarks
TC-2.5.11.1 | Enter a new password | passsword= FYPrecs!23 | The password field should be filled but the password should not be seen and the re-enter field should remainblank | Password field shows the password entered in small black dots and re-enter field is still blank | Pass | nil
TC-2.5.11.2 | enter the same password in re-enter password field | passsword= FYPrecs!23 | The re-enter password field should be filled but the password should not be seen | Re-enter password field shows the password entered in small black dots | Pass | nil
TC-2.5.11.3 | Click "update" | nil | RECS should successfully update and store my new password and redirect me back to login page | RECS redirects user back to login page | Pass | nil
TC-2.5.11.4 | Test new password at login | email = aqmal1199@gmail.com passsword= FYPrecs!23 | RECS should successfully update and store my new password hence I should be able to go to the 2FA verification page | The login was successful and user is directed to the 2FA verification page | Pass | nil